P4 Association Website

SCRUM Best Practices

- Define roles within the SCRUM team, considering the additional rules below in “Form an Opportunity-Team”.
- Declare and write down
  - Team Contract: roles, meetings, goals (team contract file)
  - Personal goals: technical, team, work-life balance (personal contract file)
- Plan daylies, review meetings with the product owner and of course a retrospection meeting at the end of the project, which reflects the outcome of the website, the team contract, goal(s), the good, the bad and the ugly. Write down a protocol.
- Crisp Daily
  - Each person declares:
  - What she*he did last.
  - What she*he will do next.
  - What kind of problems or questions may block the progress of her*his tasks.
- One person moderates the Daily and organizes solutions to problems and questions.

Organize yourselves with the help of Trello, using like “backlog”, “to do”, “in progress” and “done” as workflow categories.

Work on the project only during office hours – rest and do other things privately.

Form an Opportunity-Team

- All team members are Web Devs.
- A trainer is the product owner.
- A group speaker (team chef, scrum master) represents the team towards other teams and the product owner.
- A beginner Web Dev is also called a “Dev Junior”.
- A Mate helps a Junior.
- Important for mates and team chefs: While supporting others, do not neglect your own learning path and your development tasks!
- Declare the roles in the Team Contract - see “SCRUM Best Practices”.